{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["PBI"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"PBI","index":0,"n_rows":27,"n_cols":13,"rows_kept":27,"cut":false,"hidden":false,"merged":[[26,0,29,9],[1,0,5,0],[1,1,2,1],[4,1,5,1],[6,1,9,1],[10,1,13,1],[14,1,15,1],[19,1,22,1],[6,0,22,0],[16,1,18,1]]}
["Category","Module","Function & Page","Description","Priority","Order","T Est.","P Est.","A Est.","AssignedTo","Status","BeginDate","DoneDate"]
["RM","需求调研分析","业务调研",null,1,1,null,null,null,"卢卫国",null,null,"2016-05-23"]
[null,null,"调研分析",null,1,1,null,null,null,"卢卫国",null,null,"2016-06-03"]
[null,"技术可行性及原型验证","简历文档解析技术选择及验证",null,1,1,null,null,null,"方晨、汪祚一",null,null,"2016-06-03"]
[null,"需求说明书","需求说明书定义",null,1,2,null,null,null,"卢卫国、周妃",null,null,"2016-06-10"]
[null,null,"需求评审和变更处理",null,3]
["Feature","简历导入与更新","简历文档解析与导入","对来源于不同站点（51，猎聘)、不同文档类型的简历（包括Word,Html格式等）进行精确解析后，然后导入到简历库，导入的过程要提醒重复简历（姓名、邮箱和手机）\n备注：一期为51的word格式",1,2]
[null,null,"简历批量导入","一次性导入多个简历",1,2]
[null,null,"简历一键导入","当前操作模式是首先下载简历，然后上传简历，后续可以做成插件模式，一键导入",3]
[null,null,"简历更新维护","提供简历更新页面，允许用户直接或者在简历导入时对部分字段进行更新",2,6]
[null,"项目管理","项目创建","以项目形式来管理招聘需求，需求要明细到具体人员级别的要求",1,3]
[null,null,"项目更新",null,1,3]
[null,null,"项目简历关联","在上传简历的同时，可以同时选择对应的项目，从而将简历和项目关联起来",1,3]
[null,null,"项目简历智能匹配","创建项目的同时，可以应用智能匹配选项，由系统根据一定的条件来根据当前简历库和项目要求筛选简历",3]
[null,"简历搜索与导出","简历搜索","支持关键字，进行简历的匹配和搜索\n搜素项需要业务给出",1,4]
[null,null,"简历导出","生成公司对外标准格式的简历",1,5]
[null,"面试管理","面试反馈","电话、公司现场、客户现场的面试记录和管理",2,7]
[null,null,"面试预约",null,3]
[null,null,"面试跟踪",null,3]
[null,"后台管理","配置管理","字典和模板的配置",3]
[null,null,"用户管理","业务用户、管理员",3]
[null,null,"权限管理",null,3]
[null,null,"报表管理","项目报表、招聘报表、其他报表",3]
[]
[]
[]
["1、Order：项目工作的先后顺序（同样顺序的需要一起发布）"]